## Sheet1
Dylan Roy

Start Time	End Time	Time Spent	Total time	Quick summary of work
10/04/2021 04:15 PM	10/04/2021 04:20 PM	00:05:00	00:05:00	Initialized Time Log
10/06/21 03:00 PM	10/06/21 03:45 PM	00:45:00	00:50:00	Met with customer; overall idea of project
10/11/21 03:50 PM	10/11/21 04:00 PM	00:10:00	01:00:00	Group meeting (minus Stephen)
10/12/21 03:00 PM	10/12/21 03:30 PM	00:30:00	01:30:00	Meeting with client
10/13/21 04:00 PM	10/13/21 04:15 PM	00:15:00	01:45:00	Created outline document of our project for group
10/16/21 01:15 PM	10/16/21 01:45 PM	00:30:00	02:00:00	Research wpa_supplicant, looking into FreeBSD wifi protocol
10/18/21 09:00 AM	10/18/21 10:40 AM	01:40:00	03:40:00	Connect to WPA2-EAP network via wpa_sup→ no avail
10/19/21 03:00 PM	10/19/21 03:05 PM	00:05:00	03:45:00	Short meeting with Phil
10/20/21 03:00 PM	10/20/21 03:50 PM	00:50:00	04:35:00	Group meeting (minus Stephen); worked on Vision and Scope document collboratively
10/26/21 03:00 PM	10/26/21 03:15 PM	00:15:00	04:50:00	Meeting with client
10/27/21 10:15 AM	10/27/21 10:45 AM	00:30:00	05:20:00	Attempted to install NetBSD in lab, needed new image
10/27/21 12:10 PM	10/27/21 12:50 PM	00:40:00	06:00:00	Installed NetBSD, started configuring
10/27/21 02:50 PM	10/27/21 04:10 PM	01:20:00	07:20:00	NetBSD configuration and troubleshooting… SUCCESS!
10/29/21 04:25 PM	10/29/21 05:40 PM	01:15:00	08:35:00	Vision and Scope Work
10/30/21 02:30 PM	10/30/21 03:15 PM	00:45:00	09:20:00	Wrote Vision and Scope Peer Review
11/02/21 03:00 PM	11/02/21 03:15 PM	00:15:00	09:35:00	Meeting with Nelson
11/08/21 02:30 PM	11/08/21 03:00 PM	00:30:00	10:05:00	Group meeting
11/09/21 01:00 PM	11/09/21 02:00 PM	01:00:00	11:05:00	Success connection to EAP Network utilzing wpa_suppicant (must remember DHCP module)
11/09/21 03:00 PM	11/09/21 03:25 PM	00:25:00	11:30:00	Meeting with client
11/10/21 10:15 AM	11/10/21 10:45 AM	00:30:00	12:00:00	wpa_supplicant research
11/14/21 01:20 PM	11/14/21 02:40 PM	01:20:00	13:20:00	SRS: Features mostly done
11/15/21 03:40 PM	11/15/21 04:25 PM	00:45:00	14:05:00	Researched wpa_supplicant C library
11/18/21 08:30 AM	11/18/21 09:45 AM	01:15:00	15:20:00	Finished features and nonfunctional
11/20/21 08:30 AM	11/20/21 09:15 AM	00:45:00	16:05:00	Reviewed Stephen’s work; made some minor changes
11/21/21 03:30 PM	11/21/21 05:30 PM	02:00:00	18:05:00	Peer eval and just in case documents for if my teammates don’t finish
11/22/21 08:30 AM	11/22/21 09:00 AM	00:30:00	18:35:00	Fixing some egregious errors in my group mates’ work and mitigating clear lack of understanding…
11/30/21 03:00 PM	11/30/21 03:15 PM	00:15:00	18:50:00	Meeting with Nelson
12/02/21 09:50 AM	12/02/21 10:30 AM	00:40:00	19:30:00	Write the Milestone 1 document
12/02/21 04:15 PM	12/02/21 04:40 PM	00:25:00	19:55:00	Group meeting over milestone 1
12/02/21 06:20 PM	12/02/21 07:00 PM	00:40:00	20:35:00	Rewrite Milestone 1 based on group meeting

01/08/22 08:35 AM	01/08/22 10:35 AM	02:00:00	02:00:00	Draft of quarter plan; begin api scaffolding
01/10/22 02:30 PM	01/10/22 04:35 PM	02:04:59	04:05:00	Turn-in Initial Client contact; work on testing plan; api scaffolding → ready for implementation; made just-in-case writeup of Stephen and Kevin’s sections of testing plan
01/11/22 10:05 AM	01/11/22 11:05 AM	01:00:00	05:05:00	Start peer review.. may have to edit depending on if group mates work….
01/11/22 03:00 PM	01/11/22 03:15 PM	00:15:00	05:20:00	Client meeting
01/11/22 03:30 PM	01/11/22 04:30 PM	01:00:00	06:20:00	Help Stephen figure out NetBSD
01/11/22 12:20 PM	01/11/22 12:30 PM	00:10:00	06:30:00	Finalize Planning docs and turn in
01/11/22 02:00 PM	01/11/22 02:10 PM	00:10:00	06:40:00	Group meeting
01/12/22 08:57 AM	01/12/22 09:00 AM	00:03:00	06:43:00	Modify makefile
01/14/22 08:00 AM	01/14/22 10:55 AM	02:55:00	09:38:00	Setup remote in lab, some work on api implementation
01/17/22 09:45 AM	01/17/22 10:15 AM	00:30:00	10:08:00	API implementation… got disconnected
01/17/22 04:00 PM	01/17/22 04:30 PM	00:30:00	10:38:00	API implementation… disconnect again, but have wpa_ctrl now
01/18/22 12:25 PM	01/18/22 02:00 PM	01:35:00	12:13:00	Attempting to link wpa_supplicant. No Success, getting close
01/19/22 08:00 AM	01/19/22 10:10 AM	02:10:00	14:23:00	Got wpa_supplicant linked. Client meeting with Phil
01/19/22 02:00 PM	01/19/22 02:15 PM	00:15:00	14:38:00	Group meeting
01/20/22 08:50 AM	01/20/22 10:55 AM	02:05:00	16:43:00	Work on API: Successfully interact with wpa_supplicant, list networks, create config file
01/24/22 10:00 AM	01/24/22 10:15 AM	00:15:00	16:58:00	Work on API
01/25/22 10:00 AM	01/25/22 10:46 AM	00:46:00	17:44:00	Work on API
01/25/22 11:30 AM	01/25/22 12:42 PM	01:12:00	18:56:00	Work on API: Listing networks functional; discovered connecting and configuring should be easier than anticipated
01/26/22 10:00 AM	01/26/22 10:15 AM	00:15:00	19:11:00	Meeting with client
01/26/22 10:30 AM	01/26/22 12:00 PM	01:30:00	20:41:00	Work on API; list configured networks working; attempting to troubleshoot adding a network configuration
01/26/22 12:50 PM	01/26/22 02:00 PM	01:10:00	21:51:00	Working on API
01/27/22 08:25 AM	01/27/22 08:30 AM	00:05:00	21:56:00	Constructed outline for MS2 for group
01/27/22 10:00 AM	01/27/22 10:35 AM	00:35:00	22:31:00	Worked on MS2 and changing development plan
01/27/22 11:15 AM	01/27/22 11:50 AM	00:35:00	23:06:00	Peer Eval
01/28/22 03:30 PM	01/28/22 03:45 PM	00:15:00	23:21:00	Wrap up MS2 document and submit
01/31/22 10:20 AM	01/31/22 12:45 PM	02:25:00	25:46:00	Work on API
02/01/22 09:50 AM	02/01/22 12:20 PM	02:30:00	28:16:00	Work on API
02/02/22 10:00 AM	02/02/22 10:15 AM	00:15:00	28:31:00	Client Meeting
02/02/22 10:20 AM	02/02/22 12:10 PM	01:50:00	30:21:00	Work on API: wpa_supp doesn’t like psks and current method of removing all network entries doesn’t allow future writes
02/02/22 03:00 PM	02/02/22 03:30 PM	00:30:00	30:51:00	Group meeting; help Stephen with wpa_supplicant issues
02/04/22 10:50 AM	02/04/22 11:30 AM	00:40:00	31:31:00	Work on API; wpa_supplicant isn’t behaving and I can’t figure it out remotely…
02/07/22 10:00 AM	02/07/22 12:45 PM	02:45:00	34:16:00	Work on API; cleanNetworks still not working well… refactored testing cases, started implementing ssid isolation in listAvailable
02/08/22 10:00 AM	02/08/22 12:10 PM	02:10:00	36:26:00	Work on API; cleanNetworks works, started on deleteNetowrks… getNetworkID needs work; psk’s are now supported!
02/09/22 10:00 AM	02/09/22 10:15 AM	00:15:00	36:41:00	Client Meeting
02/10/22 06:55 AM	02/10/22 07:30 AM	00:35:00	37:16:00	Milestone 3 Initialization and contribution
02/10/22 08:45 AM	02/10/22 10:30 AM	01:45:00	39:01:00	Peer Eval, Work on API: got deleteNetwork working, started thinking on edit network
02/11/22 02:35 PM	02/11/22 02:50 PM	00:15:00	39:16:00	Wrap up MS3 document and submit; group meeting
02/15/22 10:15 AM	02/15/22 10:45 AM	00:30:00	39:46:00	Small changes to API; mostly warning addressing and test output cleanup
02/16/22 07:30 AM	02/16/22 08:40 AM	01:10:00	40:56:00	Lab machine having issues, didn’t succeed in resolving them. Implemented editNetwork
02/16/22 10:00 AM	02/16/22 10:45 AM	00:45:00	41:41:00	Client meeting; attempt to troubleshoot lab machine.. success!
02/16/22 01:05 PM	02/16/22 01:15 PM	00:10:00	41:51:00	Week 6 summary and submission
02/16/22 02:00 PM	02/16/22 02:10 PM	00:10:00	42:01:00	Group meeting
02/17/22 08:45 AM	02/17/22 10:45 AM	02:00:00	44:01:00	Work on the API: Added a debug compile option to test; started on figuring out how to include encryption for psks and passwords
02/22/22 10:00 AM	02/22/22 12:40 PM	02:40:00	46:41:00	Work on API; changing strategy for implementing hashing
02/22/22 03:00 PM	02/22/22 04:15 PM	01:15:00	47:56:00	Work on API.. get hashing to work… and success
02/23/22 10:00 AM	02/23/22 10:15 AM	00:15:00	48:11:00	Client Meeting
02/23/22 10:15 AM	02/23/22 12:00 PM	01:45:00	49:56:00	Work on API: Finished implementing psk hashing.. pwd hashing is not worth the minimal benefit
02/23/22 01:40 PM	02/23/22 01:50 PM	00:10:00	50:06:00	Week 7 summary
02/23/22 02:00 PM	02/23/22 02:10 PM	00:10:00	50:16:00	Group meeting → no Stephen
02/24/22 06:30 PM	02/24/22 07:30 PM	01:00:00	51:16:00	Milestone 4 initialization; completed peer eval
02/24/22 07:10 PM	02/24/22 07:20 PM	00:10:00	51:26:00	Milestone 4 wrap up and turn in
02/28/22 10:00 AM	02/28/22 11:50 AM	01:50:00	53:16:00	Work on API
03/01/22 10:00 AM	03/01/22 12:15 PM	02:15:00	55:31:00	Work on API: editNetworks is causing me problems….
03/02/22 10:00 AM	03/02/22 10:15 AM	00:15:00	55:46:00	Client meeting
03/02/22 10:15 AM	03/02/22 10:55 AM	00:40:00	56:26:00	Work on API: got editNetwork working, changed autoConf over to wpa_ctrl
03/02/22 01:10 PM	03/02/22 01:35 PM	00:25:00	56:51:00	Work on API→ merge features into master; weekly summary
03/03/22 08:45 AM	03/03/22 10:00 AM	01:15:00	58:06:00	Work on API: It is practically finished.
03/06/22 12:05 PM	03/06/22 12:30 PM	00:25:00	58:31:00	Help Stephen figure out why the CLI isn’t working: There was no problem, just terrible user design
03/08/22 11:00 AM	03/08/22 01:00 PM	02:00:00	60:31:00	Improve API output: finished listAvailable; listConfigured not as trivial?
03/09/22 10:00 AM	03/09/22 11:25 AM	01:25:00	61:56:00	Client Meeting
03/09/22 01:20 PM	03/09/22 02:25 PM	01:05:00	63:01:00	Work on API and … maybe?
03/09/22 02:25 PM	03/09/22 02:30 PM	00:05:00	63:06:00	Week summary
03/10/22 08:55 AM	03/10/22 09:30 AM	00:35:00	63:41:00	Initialize Milestone 5
03/11/22 01:30 PM	03/11/22 01:50 PM	00:20:00	64:01:00	Finish Milestone 5, do peer review
03/11/22 01:50 PM	03/11/22 02:30 PM	00:40:00	64:41:00	Begin presentation work

04/01/22 11:20 AM	04/01/22 11:45 AM	00:25:00	00:25:00	Initialize and work on milestone 6/quarter plan
04/04/22 02:00 PM	04/04/22 03:45 PM	01:45:00	02:10:00	Work on API output; client meeting; moved api test and turned api into library
04/05/22 09:45 AM	04/05/22 11:40 AM	01:55:00	04:05:00	Rename API to ‘surf’ and update in appropriate places; added man page documentation for surf
04/05/22 02:15 PM	04/05/22 02:20 PM	00:05:00	04:10:00	Team meeting. No Stephen
04/06/22 07:10 AM	04/06/22 07:45 AM	00:35:00	04:45:00	Work on MS-6 and peer review
04/06/22 02:10 PM	04/06/22 02:30 PM	00:20:00	05:05:00	Finish MS-6
04/07/22 10:00 AM	04/07/22 11:30 AM	01:30:00	06:35:00	Added signal to listAvailable, improved surf testing execution, worked on a logo design
04/11/22 02:35 PM	04/11/22 03:10 PM	00:35:00	07:10:00	Client meeting
04/12/22 10:45 AM	04/12/22 11:45 AM	01:00:00	08:10:00	Surf makefiles to BSDMake
04/12/22 01:50 PM	04/12/22 02:40 PM	00:50:00	09:00:00	BSDMake stuff
04/13/22 02:00 PM	04/13/22 02:10 PM	00:10:00	09:10:00	Weekly Summary
04/15/22 10:45 AM	04/15/22 11:45 AM	01:00:00	10:10:00	Changed surf’s error message handling to be more streamlined. Little changes too
04/18/22 10:45 AM	04/18/22 11:50 AM	01:05:00	11:15:00	Makefile modification and debug output fixing
04/18/22 02:00 PM	04/18/22 02:00 PM	00:00:00	11:15:00	Error testing and client meeting