## Sheet1
TASK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Milestone 1:
Create Project Skeleton
Interact With Wi-Fi System
Compile Program
Milestone 2:
Implement wpa client
Thoroughly Test Program
Deploy wpa client on VM
Milestone 3:
Implement TUI Component
Throughly Test Program
Additional Security Testing
Milestone 4:
Additional Security Testing
Meet With Stakeholders
Test Program on NetBSD
Milestone 5:
Implement GUI Component
Additional User Experience
Formally Deploy Product