## Sheet1
Stephen Loudiana
Start Time | End Time | Time Spent | Total time | Quick summary of work
10/15/2021 11:00 A.M. | 10/15/2021 1:00 P.M. | 2:00 | 2:00 | Thoroughly understanded project scope and researched NetBSD
10/17/2021 10:00 A.M. | 10/17/2021 10:10 A.M. | 0:10 | 2:10 | Wrote a quick email to www@NetBSD.org and spoke with secretary
10/21/2021 09:21 A.M. | 10/21/2021 11:21 A.M. | 2:00 | 4:10 | Worked on background.tex and business_context.tex
10/27/2021 1:00 P.M. | 10/27/2021 2:00 P.M. | 1:00 | 5:10 | Created gantt chart and made additional small changes to scope
11/18/2021 4:00 P.M. | 11/18/2021 6:00 P.M. | 2:00 | 7:10 | Worked on introduction and thoroughly understand software requirements and features
11/19/2021 9:30 A.M. | 11/19/2021 11:00 A.M. | 1:30 | 8:40 | Created use cases in models file
11/21/2021 5:00 P.M. | 11/21/2021 8:00 P.M. | 3:00 | 11:40 | Finished writing description and external interfaces
01/12/2022 3:00 P.M. | 01/12/2022 7:00 P.M. | 5:00 | 5:00 | Set up NetBSD on VM, wrote a makefile. Makefile had to be specific, took too much time. (I will probably work over 40 hours this quarter, but I will document all time spent).
01/17/2022 1:50 P.M. | 01/17/2022 4:50 P.M. | 3:00 | 8:00 | Began work on designing command line interface. Further set up NetBSD specifics. Started Coding.
1/18/2022 1:05 P.M. | 01/18/2022 4:05 P.M. | 3:00 | 11:00 | Made no progress. Can't work on it any longer.
1/20/2022 12:32 P.M. | 01/20/2022 3:19 P.M. | 3:00 | 14:00 | Started design of CLI and added many functions. Updated makefile and files for cli component.
1/21/2022 10:23 A.M. | 01/21/2022 11:14 A.M. | 0:30 | 14:30 | More protocol implementation. Will work on it later.
1/23/2022 4:00 P.M. | 01/23/2022 4:30 P.M. | 0:30 | 15:00 | Fixed a few things, did some error checking. Ready to start processing commands from API.
1/24/2022 11:00 A.M. | 01/24/2022 1:00 P.M. | 2:00 | 17:00 | Made it more secure. Can't break the cli, ready for API implementation.
1/25/2022 11:08 A.M. | 01/25/2022 12:41 P.M. | 1:33 | 18:33 | Added some macros. Made it more secure. Will start API implementation during Milestone 2
01/30/2022 11:36 A.M. | 01/30/2022 12:18 P.M. | 0:42 | 19:09 | Spent some time trying to get api methods to run but having some difficulty. Will meet with team this week to start getting the api to interact with the cli.
02/02/2022 11:18 A.M. | 02/02/2022 2:36 P.M. | 3:18 | 22:27 | Finally connected and started testing api methods on wwu netbsd machine. No need for virtual machine at all.
02/03/2022 11:00 A.M. | 02/03/2022 12:30 P.M. | 1:30 | 23:57 | Spent time working to compile program. Still getting errors. Will attempt to get help tomorrow.
02/05/2022 11:18 A.M. | 02/05/2022 12:31 P.M. | 1:13 | 25:10 | Worked on api implementation with cli file
02/06/2022 12:35 P.M. | 02/06/2022 3:06 P.M. | 2:30 | 27:40 | Worked on more api implemention, working through config auto
02/10/2022 10:51 A.M. | 02/10/2022 11:02 A.M. | 0:10 | 27:50 | Completed milestone write up for miltestone 3
02/25/2022 12:16 P.M. | 02/25/2022 12:45 P.M. | 0:30 | 28:20 | Completed milestone 4 write - up and peer review
03/03/2022 10:53 A.M. | 03/03/2022 4:35 P.M. | 5:40 | 34:00 | Implemented all methods associated with cli. Tested methods on netbsd operating system. Still need to do additional testing.
03/06/2022 10:08 A.M. | 03/06/2022 1:38 P.M. | 3:30 | 37:30 | Did some testing. Added comments. Additional testing still required. Added help method to display commands.
03/06/2022 3:08 P.M. | 03/06/2022 4:38 P.M. | 1:30 | 39:00 | Edited some commands. Still testing interface but will likely save a majority of testing for next quarter.
03/09/2022 4:09 P.M. | 3/9/2022 5:12 P.M. | 1:00 | 40:00 | Attempted to find the source of the seg fault but no luck. Doesn't set fault when working on a separate machine. Will need to debug and test next quarter. Spent a considerable amount of time going through my code.
04/04/2022 10:45 P.M.